## Sheet1
Rolleston on Dove Parish Council Neighbourhood Plan Project Plan
Version 30/06/18
Item Number | General Plan | 2017 |  |  |  |  | 2018
|  | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | Npvember | December | Jann - 19 | 2019-02-01
1 | Evidence Building | bar: 2017 August to 2018 February
2 | Key Stakeholder Engagement | bar: 2017 August to 2018 February
3 | Policy mapping | 2017 November: 20th
4 | Issues, Options, Solutions Eng. | bar: 2017 September to 2018 January
5 | Policy/Proposals Formulation | bar: 2017 September to 2018 January
6 | Plan Writing | bar: 2017 September to 2018 January
7 | Draft Plan | bar: 2018 January
8 | Screening (SEA/HRA) | bar: 2018 February to 2018 April
9 | Regulation 14 6 week period | 2018 April: 30th; 2018 June: 14th
10 | Feedback | bar: 2018 May to 2018 June
11 | Analysis of responses | bar: 2018 June
12 | Modify / Finalise Plan | bar: 2018 June
13 | Regulation 14 6 week period - 2ND period | 2018 September: Sept 24th; 2018 October: October | Nov. 6th
14 | Feedback
15 | Analysis of responses
16 | Modify / Finalise Plan | [16 empty] | 10th Dec
17 | Revising Consultation Statement | [16 empty] | 10th Dec
18 | Revising Basic Conditions Statement | [16 empty] | 10th Dec | Withdraw letter 10th Dec
19 | Submission to LPA | [16 empty] | 17th Dec
20 | Regulation 16 | [16 empty] | 17th Dec
21 | Independent Examination
22 | Modification
23 | Publicise Referendum (28 days)
24 | Referendum
25 | Plan is 'made'
| Community Engagement Plan | 2017 August: 2017; 2018 January: 2018
1 | Pop up community events | 2018 May: 19th; 2018 October: Oct 14h
2 | Website Updates | [16 empty] | 17th Dec | bar: 2018 May; 2018 September
3 | Parish Council Newsletter | bar: 2018 May; 2018 September
4 | Rollestonian | bar: 2018 May
5
6
7
8
10
| Steering Group Meetings | 2017 August: 2017; 2018 January: 2018
1 | Steering Group Meetings | 14th | 4th/25th | 16th/30th | 20th | 18th | 12th/15th/29th | 12th/26th | 2nd/ 23rd | 13th/20th | 14th/19th |  | 15th/22nd/27th | 2nd. 13th | 14th | ` | 23rd/30th
2 | Working Group Meetings
Key:
Statutory Process
Delivery Period
Note on M43: Mr Gooding:
Note on N43: Mr Gooding: